## Master Project Schedule
MASTER PROJECT SCHEDULE TEMPLATE
| PROJECT TITLE |  | START DATE
|  |  | 2024-01-02 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
|  |  | 2024-03-26 |  |  | 85
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | Complete |  | 2024-01-02 | 2024-02-09 | 39 |  | Not Started
1.1 | – Project Charter | Complete |  | 2024-01-02 | 2024-01-11 | 10 |  | In Progress
1.1.1 | –– Project Charter Revisions | Complete |  | 2024-01-07 | 2024-01-11 | 5 |  | Complete
1.2 | – Research | Complete |  | 2024-01-10 | 2024-02-23 | 45 |  | On Hold
1.3 | – Projections | Complete |  | 2024-01-10 | 2024-01-20 | 11
1.4 | – Stakeholders | Complete |  | 2024-01-16 | 2024-01-29 | 14
1.5 | – Guidelines | In Progress |  | 2024-01-19 | 2024-02-01 | 14
1.6 | – Project Initiation | In Progress |  | 2024-01-22 | 2024-02-09 | 19
2 | PROJECT DEFINITION AND PLANNING | In Progress |  | 2024-01-28 | 2024-02-14 | 18
2.1 | – Scope & Goal Setting | On Hold |  | 2024-01-28 | 2024-02-06 | 10
2.2 | – Budget | In Progress |  | 2024-01-31 | 2024-02-02 | 3
2.3 | – Communication Plan | In Progress |  | 2024-02-04 | 2024-02-12 | 9
2.4 | – Risk Management | Complete |  | 2024-02-06 | 2024-02-14 | 9
3 | PROJECT LAUNCH & EXECUTION | Complete |  | 2024-02-18 | 2024-03-26 | 38
3.1 | – Status & Tracking | In Progress |  | 2024-02-18 | 2024-02-20 | 3
3.2 | – KPIs | In Progress |  | 2024-02-18 | 2024-02-23 | 6
3.2.1 | –– Monitoring | In Progress |  | 2024-02-18 | 2024-02-26 | 9
3.2.2 | –– Forecasts | Not Started |  | 2024-02-21 | 2024-02-23 | 3
3.3 | – Project Updates | Not Started |  | 2024-02-22 | 2024-02-23 | 2
3.3.1 | –– Chart Updates | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4 | PROJECT PERFORMANCE / MONITORING | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4.1 | – Project Objectives | In Progress |  | 2024-02-25 | 2024-02-28 | 4
4.2 | – Quality Deliverables | On Hold |  | 2024-02-26 | 2024-03-03 | 7
4.3 | – Effort & Cost Tracking | Not Started |  | 2024-02-25 | 2024-03-06 | 11
4.4 | – Project Performance | Not Started |  | 2024-03-03 | 2024-03-26 | 24

## BLANK - Master Project Schedule
MASTER PROJECT SCHEDULE
| PROJECT TITLE |  | START DATE
| Portafolio de proyectos personales |  | 18/02/25 |  |  | PROJECT DURATION
| PROJECT MANAGER |  |  |  |  | in days
| Oliver Suarez Mora |  | 2025-01-05 |  |  | #VALUE!
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | Fase de analisis | Complete |  |  |  | 1 |  | Not Started
1.1 | Investigar PostgreSQL/MongoDB | Not Started | Samantha | 2025-02-20 | 17 marzo | #VALUE! |  | In Progress
1.1.1 | Investigar Node.js/Express o Django | Not Started | Oliver | 2025-02-21 | 17 marzo | #VALUE! |  | Complete
1.2 | Investigar React.js o Vue.js | Not Started | Karen | 2025-02-22 | 17 marzo | #VALUE! |  | On Hold
1.3 | Fase de diseño | Not Started |  |  |  | 1
1.4 | Configurar entorno de desarrollo y GitHub | Not Started | Samantha, Oliver,Karen | 26 febrero | 27 febrero | #VALUE!
1.5 | Maqueta inicial del proyecto | Not Started | Samantha, Oliver,Karen
1.6 | Diseñar y crear base de datos inicial (usuarios, proyectos) | Not Started | Samantha | 18 marzo | 31 marzo | #VALUE!
1.6 | Fase de implementacion | Not Started |  |  |  | 1
2 | Maquetar frontend y crear diseño inicial de pantallas |  | Karen | 18 marzo | 31 marzo | #VALUE!
2.1 | Scope & Goal SettingConfigurar backend con API básica (usuarios, autenticación) | Not Started | Oliver | 1 abril | 14 abril | #VALUE!
2.2 | Implementar autenticación de usuarios (registro, login, JWT/sesiones) | Not Started | Oliver | 1 abril | 14 abril | #VALUE!
2.3 | Crear pantallas de autenticación en frontend (registro/login) | Not Started | Karen | 1 abril | 14 abril | #VALUE!
2.4 | Implementar CRUD de proyectos en backend | Not Started | Oliver | 1 abril |  | #VALUE!
3 | Diseñar e implementar página de proyectos en frontend |  | Karen |  |  | 1
3.1 | Fase de integracion | Not Started |  |  |  | 1
3.2 | Conectar backend con API de GitHub (importar repositorios) | Not Started | Oliver |  |  | 1
3.2.1 | Mejorar frontend con detalles de proyectos y ajustes UI | Not Started | Karen |  |  | 1
3.2.2 | Fase de pruebas | Not Started |  |  |  | 1
3.3 | Pruebas finales de base de datos y optimización de consultas | Not Started | Samantha |  |  | 1
3.3.1 | Pruebas finales de backend y seguridad (XSS, SQL Injection) | Not Started | Oliver |  |  | 1
4 | Pruebas finales de frontend y correcciones UI/UX |  | Karen |  |  | 1
4.1 | Fase de Mantenimiento | Not Started |  |  |  | 1
4.2 | Desplegar la base de datos en servidor (AWS, Render, Supabase) | Not Started | Samantha |  |  | 1
4.3 | Desplegar backend en servidor (AWS, Vercel, Heroku) | Not Started | Oliver |  |  | 1
4.4 | Desplegar frontend en Vercel o Netlify | Not Started | Karen |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.